## Summary
Project Name: | SavorIQ
Studio #: | #SDS02_Wed_3_6
Mentor: | Name
Team Lead(s): | Nicholas Solomos
Week | Progress
Week 1 - Studio Introduction and Project Brief | 100%
Week 2 - Pre-Sprint Preparation | 0%
Week 3 - Sprint 0 Week 1 | 0%
Week 4 - Sprint 0 Week 2 | 0%
Week 5 - Sprint 1 Week 1 | 0%
Week 6 - Sprint 1 Week 2 | 0%
Week 7 - Sprint 2 Week 1 | 100%
Week 8 - Sprint 2 Week 2 | 0%
STUVAC WEEK (1) | 100%
Week 9 - Sprint 3 Week 1 | 0%
Week 10 - Sprint 3 Week 2 | 0%
Week 11 - Sprint 4 Week 1 | 0%
Week 12 - Sprint 4 Week 2 | 0%
STUVAC (2) - Extra Week Before Final Submission (USE IT WISELY!) | 66.67%
Exam Period | 100%

## Week 1
Week 1 - Studio Introduction and Project Brief
Check Box | Task | Description
TRUE | Attend Client’s Project Presentation | Attend the Lecture in the first week to hear about all the available projects that you can choose from.
TRUE | Read Project Briefs | Read the Project Briefs available in Microsoft Teams.
TRUE | Agile Readiness Quiz | Complete the ‘Agile Process Assessment Checklist’ Quiz on Canvas.
1
Note on B2: Tick the task when completed!

## Week 2
Week 2 - Pre-Sprint Preparation
Check Box | Task | Description
TRUE | Get Allocated to Your Team | Get allocated to your Team in class on Wednesday.
TRUE | Set up Communication Spaces/Software | Set up Project Management Tool (e.g. Jira, GitHub Projects, Trello), Documentation Tool, Microsoft Teams and/or Google Drive spaces.
TRUE | Define Team Roles and Stand-up Time | Clearly define your team roles. Record them onto the Team's choice of Documentation Tool. Assign yourselves into the Groups on Canvas. Create a Weekly stand-up meeting for your Team. This could be during class or outside – as long as it is before your client meeting.
TRUE | Team's Project Brief | Start drafting your Team’s Project Brief (template avaliable on Teams).
TRUE | Read Project Brief | Read through your project brief as a Team.
TRUE | Software Requirements and Specification Documentation | Start drafting the ‘Software Requirements and Specification’ Documentation in a Google Drive or Microsoft Teams space. In particular, the following sections: Project Purpose (Problem Statement, Goals and Objectives, Success Criteria), Project Scope (Project Boundary Diagram, In-Scope, Out of Scope), Assumptions, Risks, Issues, Constraints, Dependencies, System Users and Channels, Functional Requirements (Functional Requirements, User Story Narratives, User Story Map), Data Requirements (Conceptual Data Model, Data Dictionary), Non-Functional Requirements (Requirements Specifications, User Interface Requirements). Template available on Canvas – under Assessment 3.
TRUE | Create Questions for Your Client | Create a list of questions for your first Client meeting. These should include any questions that the Team needs further clarification on.
TRUE | Draft First Client Email | Team Leads, draft your first client email and get feedback from your Mentor before the end of the Studio.
TRUE | Establish the First Client Meeting | Once the External Engagement Partner (Harrison) has connected the Team Leads with the Client, establish the first Client meeting. Ideally, this meeting should be a recurring meeting from at least 45-minutes after the start of your SDS session.
TRUE | Create User Stories | Draft User Stories from the Project Brief. Hint: it is best if everyone creates at least two user stories each, that way you don’t miss anything and everyone’s working on A2 already!
TRUE | Create First User Stories (Jira, Trello or GitHub Projects) | In your Teams' choice of Project Management Tool, create a product backlog (all the User Stories). Note: make sure you create User Stories – not Issues!
TRUE | Create First Documentation Pages (Documentation Tool, Google Docs, Teams) | Add the list of questions for your Client into your Teams' choice of Documentation Tool, a page for the names and roles of each member of your Team, and a page for the Communication and Collaboration Plan (include links to the relevant spaces). Also add anying else relevant too!
TRUE | Create a Meeting Agenda for the First Client Meeting | Create a meeting agenda as a guide for your first Client meeting.
TRUE | Sprint 0 Planning | Create a Sprint 0 Backlog. Discuss the planned Sprint tasks. Ensure all Team members know what the tasks involve. Add Estimated Time/Effort required for each User Story using Story Points. Hint: Story Points are needed for Burndown Charts. Note: you may discover some tasks are unnecessary or more tasks are needed to ensure a spread workload for everyone.
TRUE | Play Around with the Project Management Tool | If the Team isn’t already familiar with the Project Management Tool, play around with it. Hint: the more familiar you are with the tool, the easier it’ll be to use!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 3
Week 3 - Sprint 0 Week 1
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | First Client Meeting | Attend your first client meeting. Ensure there are minute takers. An ideal template for meeting minutes is as follows: agenda, notes, and action items. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Update Software Requirements and Specification Documentation & User Stories | Update Software Requirements and Specification Documentation and User Stories that were made last week, based on the Client’s feedback. Add acceptance criteria to your User Stories. Note: acceptance criteria are the set of criteria that your Team will use to ensure each User Story has been wholistically achieved.
TRUE | Project Brief | Create a Project Brief using the sections from the ‘Software Requirements and Specification’ document in Documentation Tool. Include the following sections: project description, current system, project objectives, scope, risks, constraints, and dependencies. The purpose of this Brief is to ensure a (written) Client sign-off on your deliverables and confirming anything in- or out-of-scope. Hint: make sure your in-scope is achievable in the project’s timeframe. Note: this helps to ensure everyone’s on the same page!
TRUE | Project Management Tool Housekeeping | Start ‘Sprint 0’ in Project Management Tool. Create ‘Epics’ to categorise the Sprint 0 User Stories, e.g., Frontend, Backend or Testing. Allocate Team members their Sprint tasks. Note: make sure the user stories are achievable for the sprint. They should be small, achievable chucks of work. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Get Client’s sign-off on Project Brief. The Client can simply comment on the Documentation Tool page as a digital sign-off. Create pages for your User Stories, Issue Tracking and Project Brief. Also add any else relevant too!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 4
Week 4 - Sprint 0 Week 2
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Make sure you have a (written) Client sign-off! The Client may want to discuss any of their concerns during this meeting. Make sure to keep an open mind. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Create Software Architecture Diagrams | Start drafting the ‘Software Architecture’ Documentation in a Google Drive or Microsoft Teams space. In particular, the following sections: High-level overall Software Architecture Diagram, Interaction Architecture (UI Designs, User Interface Map, User Journey Map), Business Architecture (Business Process Model), Information Architecture (Conceptual Data Model e.g., ERD, Data Dictionary), Application Architecture (software components, data components, hardware components), Security Architecture (e.g., MVC Architecture and explain the different components). Template available on Canvas – under Assessment 3.
TRUE | Update Project Brief, Software Requirements and Specification Documentation & User Stories | Update the Project Brief, Software Requirements and Specification Documentation and User Stories if relevant after the Client meeting.
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Assign any more tasks, if relevant. Note: each Software Architecture Diagram can be added as a ‘User Story’ in Project Management Tool! Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too!
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Sprint 1 Planning | Create a Sprint 1 Backlog. Discuss the planned Sprint tasks. Ensure all Team members know what the tasks involve. Add Estimated Time/Effort required for each User Story using Story Points. Hint: Story Points are needed for Burndown Charts. Note: you may discover some tasks are unnecessary or more tasks are needed to ensure a spread workload for everyone.
TRUE | Communication with Client (End of Every Sprint) | Team Leads, email your Client with a summary of your (latest) Sprints progression and your plans for the upcoming Sprint.
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 5
Week 5 - Sprint 1 Week 1
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Make sure you have a (written) Client sign-off! The Client may want to discuss any of their concerns during this meeting. Make sure to keep an open mind. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Software Architecture Diagrams | Continue working on the Software Architecture Diagrams. Note: feel free to drop-in to the Advisor’s consultations to get advice on these diagrams.
TRUE | Update Project Brief, Software Requirements and Specification Documentation & User Stories | Update the Project Brief, Software Requirements and Specification Documentation and User Stories if relevant after the Client meeting.
TRUE | Project Management Tool Housekeeping | Start ‘Sprint 1’ in Project Management Tool. Create ‘Epics’ to categorise the Sprint 1 User Stories, e.g., Frontend, Backend or Testing. Allocate Team members their Sprint tasks. Note: make sure the user stories are achievable for the sprint. They should be small, achievable chucks of work. Discuss when Project Management Tool tasks should be moved into “done” – e.g., after testing or acceptance criteria is checked by another member? Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too!
TRUE | General Housekeeping | Make sure all Team members have their Individual Development Environments (IDEs) set up and made a practice “Hello World!” commit (to ensure no technical difficulties later on). Ensure to document any issues (Documentation Tool Page: Issue Tracking) or questions as you go!
TRUE | Sprint 0 Retrospective | Complete a Sprint 0 Retrospective answering the following questions: What went well? What could have gone better? What will we try next? What questions do we have? Document this in Documentation Tool. Hint: it is best if everyone takes their own notes for both group and individual retrospectives, that way you don’t miss anything and everyone’s working on A2 already.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 6
Week 6 - Sprint 1 Week 2
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Create Software Architecture Diagrams | Continue working on the Software Architecture Diagrams. If possible, get the Advisor to sign off on the Software Architecture Diagrams – a written comment or email!
TRUE | Update Project Brief, Software Requirements and Specification Documentation & User Stories | Update the Project Brief, Software Requirements and Specification Documentation and User Stories if relevant after the Client meeting.
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes and Software Architectures Diagrams. Also add any else relevant too!
TRUE | Sprint 2 Planning | Create a Sprint 2 Backlog. Discuss the planned Sprint tasks. Ensure all Team members know what the tasks involve. Add Estimated Time/Effort required for each User Story using Story Points. Hint: Story Points are needed for Burndown Charts. Note: you may discover some tasks are unnecessary or more tasks are needed to ensure a spread workload for everyone.
TRUE | Communication with Client (End of Every Sprint) | Team Leads, email your Client with a summary of your (latest) Sprints progression and your plans for the upcoming Sprint.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 7
Week 7 - Sprint 2 Week 1
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Software Architecture Diagrams | Continue working on the Software Architecture Diagrams. If you haven’t already, get the Advisor to sign off on the Software Architecture Diagrams – a written comment or email!
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Start ‘Sprint 2’ in Project Management Tool. Allocate Team members their Sprint tasks. Create ‘Epics’ to categorise the Sprint 2 User Stories, e.g., Frontend, Backend or Testing. Allocate Team members their Sprint tasks. Note: make sure the user stories are achievable for the sprint. They should be small, achievable chucks of work. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes and Software Architectures Diagrams. Also add any else relevant too!
TRUE | Sprint 1 Retrospective | Complete a Sprint 1 Retrospective answering the following questions: What went well? What could have gone better? What will we try next? What questions do we have? Document this in Documentation Tool. Hint: it is best if everyone takes their own notes for both group and individual retrospectives, that way you don’t miss anything and everyone’s working on A2 already!
TRUE | Attend Assessment 1 De-Briefing led by your Mentor! | Attend the assessment 1 de-briefing led by your Mentor, sometime during your SDS Session. Note: Assessment 1 (all individual) has 2 Sprint reflections and 1 design journal.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## Week 8
Week 8 - Sprint 2 Week 2
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Software Architecture Diagrams | Continue working on the Software Architecture Diagrams. If you haven’t already, get the Advisor to sign off on the Software Architecture Diagrams – a written comment or email!
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes and Software Architectures Diagrams. Also add any else relevant too!
TRUE | Submit Assessment 1 (Individual) | Make sure you submit Assessment 1.
TRUE | Sprint 3 Planning | Create a Sprint 3 Backlog. Discuss the planned Sprint tasks. Ensure all Team members know what the tasks involve. Add Estimated Time/Effort required for each User Story using Story Points. Hint: Story Points are needed for Burndown Charts. Note: you may discover some tasks are unnecessary or more tasks are needed to ensure a spread workload for everyone.
TRUE | Mentor's Debrief for the SDS Session Project Showcase | Attend the de-briefing led by your Mentor, sometime during your SDS Session.
TRUE | Communication with Client (End of Every Sprint) | Team Leads, email your Client with a summary of your (latest) Sprints progression and your plans for the upcoming Sprint.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B2: Tick the task when completed!

## STUVAC (1)
STUVAC WEEK (1)
Check Box | Task | Description
TRUE | (Optional) Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | (Optional) Client Meeting | Attend your client meeting. Ensure there are minute takers. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | (Highly Recommended) Code Away! | Make sure your Team makes the most of this extra week in Sprint 2!
1
Note on B2: Tick the task when completed!

## Week 9
Week 9 - Sprint 3 Week 1
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Showcase a Demonstration of your working product to your Client. Make sure to get their feedback on the product. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Official Assessment 3 Documentation | Start drafting your Team’s official Assessment 3 Documentations – ‘Software Requirements and Specification’ and ‘Software Architecture’. Templates available on Canvas – under Assessment 3. Hint: you guys have been working on these sections throughout the semester!
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Start ‘Sprint 3’ in Project Management Tool. Allocate Team members their Sprint tasks. Create ‘Epics’ to categorise the Sprint 3 User Stories, e.g., Frontend, Backend or Testing. Allocate Team members their Sprint tasks. Note: make sure the user stories are achievable for the sprint. They should be small, achievable chucks of work. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too!
TRUE | Sprint 2 Retrospective | Complete a Sprint 2 Retrospective answering the following questions: What went well? What could have gone better? What will we try next? What questions do we have? Document this in Documentation Tool. Hint: it is best if everyone takes their own notes for both group and individual retrospectives, that way you don’t miss anything and everyone’s working on A2 already!
TRUE | Practice Team Presentation | Draft a Team presentation to practice in front of your Mentor within the next two weeks. Make sure to talk to your Mentor to gain a practice timeslot that works for your Team. Ensure the presentation slides include (at least): Team overview (with everyone’s pictures, names and Team roles), project overview (with a brief description of Client, project objectives and goals), project scope (in and out of scope), functional and non-functional requirements, Solution Architecture (high-level solution diagram), anything else relevant, and a demonstration of your working product. Hint: Team presentation falls under Assessment 3! Note: you may add this as a Project Management Tool ‘User Story’.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B1: Note: don’t let the Project’s scope creep anymore!
Note on B2: Tick the task when completed!

## Week 10
Week 10 - Sprint 3 Week 2
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Showcase a Demonstration of your working product to your Client. Make sure to get their feedback on the product. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Official Assessment 3 Documentation | Continue working on your Team’s official Assessment 3 Documentations – ‘Software Requirements and Specification’ and ‘Software Architecture’. Templates available on Canvas – under Assessment 3. Hint: you guys have been working on these sections throughout the semester!
TRUE | Practice Team Presentation | Perform your Team’s practice presentation to practice in front of your Mentor.
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Assign any more tasks, if relevant. Note: each Software Architecture Diagram can be added as a ‘User Story’ in Project Management Tool! Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too!
TRUE | Sprint 4 Planning | Create a Sprint 4 Backlog. Discuss the planned Sprint tasks. Ensure all Team members know what the tasks involve. Add Estimated Time/Effort required for each User Story using Story Points. Hint: Story Points are needed for Burndown Charts. Note: you may discover some tasks are unnecessary or more tasks are needed to ensure a spread workload for everyone.
TRUE | Communication with Client (End of Every Sprint) | Team Leads, email your Client with a summary of your (latest) Sprints progression and your plans for the upcoming Sprint.
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B1: Note: don’t let the Project’s scope creep anymore!
Note on B2: Tick the task when completed!

## Week 11
Week 11 - Sprint 4 Week 1
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Showcase a Demonstration of your working product to your Client. Make sure to get their feedback on the product. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Official Assessment 3 Documentation | Continue working on your Team’s official Assessment 3 Documentations – ‘Software Requirements and Specification’ and ‘Software Architecture’. Templates available on Canvas – under Assessment 3. Hint: you guys have been working on these sections throughout the semester!
TRUE | Practice Team Presentation | Perform your Team’s practice presentation to practice in front of your Mentor.
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Start ‘Sprint 4’ in Project Management Tool. Allocate Team members their Sprint tasks. Create ‘Epics’ to categorise the Sprint 4 User Stories, e.g., Frontend, Backend or Testing. Allocate Team members their Sprint tasks. Note: make sure the user stories are achievable for the sprint. They should be small, achievable chucks of work. Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too!
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Sprint 3 Retrospective | Complete a Sprint 3 Retrospective answering the following questions: What went well? What could have gone better? What will we try next? What questions do we have? Document this in Documentation Tool. Hint: it is best if everyone takes their own notes for both group and individual retrospectives, that way you don’t miss anything and everyone’s working on A2 already!
TRUE | Attend Assessment 2 De-Briefing led by your Mentor! | Attend the assessment 2 de-briefing led by your Mentor, sometime during your SDS Session. Note: Assessment 2 is all individual).
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B1: Note: don’t let the Project’s scope creep anymore!
Note on B2: Tick the task when completed!

## Week 12
Week 12 - Sprint 4 Week 2
Check Box | Task | Description
TRUE | SCRUM of SCRUM | Attend SCRUM of SCRUM. Update the whiteboard with your Teams progression.
TRUE | Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
TRUE | Client Meeting | Attend your client meeting. Ensure there are minute takers. Hint: it is best if everyone takes their own notes, that way you don’t miss anything and everyone’s working on A2 already! Showcase a Demonstration of your working product to your Client. Make sure to get their feedback on the product. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | Practice Team Presentation | If you haven’t already, perform your Team’s practice presentation to practice in front of your Mentor.
TRUE | Official Assessment 3 Documentation | Continue working on your Team’s official Assessment 3 Documentations – ‘Software Requirements and Specification’ and ‘Software Architecture’. Templates available on Canvas – under Assessment 3. Hint: you guys have been working on these sections throughout the semester!
TRUE | Project Management Tool Housekeeping | Update the progress on any assigned Sprint User Stories from last week. Assign any more tasks, if relevant. Note: each Software Architecture Diagram can be added as a ‘User Story’ in Project Management Tool! Hint: updating Project Management Tool User Stories throughout the week creates a better graph.
TRUE | Documentation Tool Housekeeping | Add Meeting Minutes. Also add any else relevant too! Note: if there are any issues, don’t forget to record them in the Issue Tracking page!
TRUE | Code Away! | If you have any remaining time in your SDS session, feel free to code away or ask your peers, colleagues, or Mentor for any assistance! Note: if there are any issues, don’t forget to record them in the Issue Tracking page and create a new Project Management Tool ticket!
TRUE | Submit Assessment 2 (Individual) | Make sure you submit Assessment 2 by midnight on Monday the 13th of May!
TRUE | Communication with Client (End of Every Sprint) | Team Leads, email your Client with a summary of your (latest) Sprints progression and your plans for the final project handover.
TRUE | Mentor Check-in | Get your Mentor to check-in with your Team during the Studio.
Note on B1: Note: don’t let the Project’s scope creep anymore!
Note on B2: Tick the task when completed!

## STUVAC (2)
STUVAC (2) - Extra Week Before Final Submission (USE IT WISELY!)
Check Box | Task | Description
TRUE | (Optional) Team Stand-Up | Complete the Team’s Stand-up (if you haven’t already).
FALSE | (Optional) Client Meeting | Attend your client meeting. Ensure there are minute takers. Showcase a Demonstration of your working product to your Client. Make sure to get their feedback on the product. Note: If you would like to record the meeting, ensure you confirm with everyone before doing so.
TRUE | (Highly Recommended) Code Away! | Make sure your Team makes the most of this extra week before final submission!
0.66667
Note on B1: Hint: start marking sure everything is finalised. Prepare for project handover.
Note on B2: Tick the task when completed!

## Exam Period
Exam Period
Check Box | Task | Description
TRUE | Assessment 3 Presentation | Team to present to Client and Mentor. See Canvas for Assessment 3 Presentation schedule.
TRUE | Submit Assessment 3 | Team Leads to submit Assessment 3 on behalf of the Team by the due date on Canvas.
TRUE | SparkPlus (Individual) | Complete SparkPlus (individually).
1
Note on B2: Tick the task when completed!